# Information Note

# EU Timber Trade Illegal Logging Initiative

## Overview

- A partnership of EU trade and developing country organisations

- Applicant: Tropical Forest Trust

- Partners: NL, Be, UK, MTC, E. Kalimantan University ….. more are welcome

- Associates: Fr, UCBD and FEBO…. more are welcome

- Total grant awarded: €3.5 million

- Duration: 5 years

- Result of evaluation: November 2004

- Begin implementation: March 2005 at the earliest

## Objectives

- Source legal tropical timber into the supply chains of NL, Be, UK and TFT members

- Indonesia, Malaysia, Gabon and Cameroon

- Technical assistance to suppliers and traders alike

- Chain of Custody, Auditing, Codes of practice

- Institutional capacity building

- Sustainable financing mechanism

## Methodology

1.Capacity building and practical timber tracking (80% of budget)

- Supplier countries

2.Voluntary codes of practice and information on legality (15%)

- Harmonisation of standards based on understanding of legislation, tracking systems and independent auditing

3.Communication of good practice and lesson-learning (5%)

- Workshops, bulletins, website, consultations

## Budget

- Staff costs for partners, local staff, regional teams, project manager, financial controller, regional coordinator – €2.6 m

- Travel costs (international and local) – €360k

- Equipment and supplies - €412k

- Local costs - €277k

- Research, publications, translation, audits, evaluation, conferences, communication - €430k

- Chain of custody investment

- EC contribution = €3.5 m (50%)

- EU TTF’s = €870k (13%)

- Market = €2.6m via a market-driven 2% price increase for legally verified timber (37%)

- Grand Total = €6.98m over 5 years

## Cofinancing  explained:

- To construct the budget, we assumed each importing partner will contribute according to the volume of tropical timber traded

- But once operational, funding for supply chain work will depend on how much importers are willing to pay

- A formula will be agreed that ensures any investment by importers in their supply chains will be matched by the EC grant

- Likely proportion will be €1 from traders = €2-4 EC grant

## Cofinancing example:

- Trader A imports plywood from Producer X in Indonesia and wants to secure verified legal timber for a govt. contract

- Producer X needs €100,000 investment in supply chain to get legally verified timber

- If Trader A pays €10,000, he will then get another €30,000 support from EC Grant

- Producer X will then pay remaining €60,000 on the basis that at least Trader A will be prepared to pay 2% more for verified legal plywood

- Producer X may be able to sell verified timber at an even higher premium to non-sponsoring traders

## Funds can be raised from:

- Member State donors (sustainable trade, development, and environment programmes)

- Federation’s own general membership fees or

- From special subscription/request

1 + 2 + 3 = €870,000

- Partners are responsible for co-ordinating fund-raising

- If they can’t raise the co-financing then we can’t get so much of the grant

## The Project Governing Board

- Partners and associates meet to establish detailed governance mechanisms

- Chaired by VVNH

- Set up application procedures for suppliers and then evaluate proposals

- Meet frequently to start with

- Manage strategic changes and policy

- Reporting forum for partners

## Who is the Tropical Forest Trust

- An NGO working for business, 5 years old

- 27 member companies in 17 countries

- Turnover in 2003 = US$ 1.1 million

- Business plan for 2004 = US$ 1.6 million

- Board members include Jysk (Denmark),Robert Dyas (UK),Kwantum (NL),Castorama (Fr)

- 27 staff in EU, Indonesia, Vietnam, Malaysia and Laos – mainly professional foresters working directly with mills and forests

- In 2004 expanding into Africa (CIB is new member)

## TFT – How They Work

- Members have to exclude illegal wood from their supply chains and get natural forests certified

- Currently using only FSC for sustainable forest management but;

- Working with MTCC in Malaysia

- Willing to work with any certification scheme their members want them to provided it meets their standards

- Project partners felt that under this project they could work with TFT because the objective is to exclude illegal wood

- TFT quoted in the EC Action Plan as an example of private sector action

## Conclusion – Project Deliverables

- Direct practical support to suppliers to achieve verifiable legal timber (183 mills)

- Common standards for legality verification

- Systems for monitoring supply chain transparency and accountability

- Objective advice for traders seeking timber from ‘risky’ countries

- Improvement in the reputation of tropical timber, and therefore the EU timber trade

- Important step toward sustainability

- 20% of tropical timber entering partner countries will be verified legal

Andy Roby, CSR Adviser, TTF – 23rd June 2004 updated on 14th December